## Slide 1
The PICASP Project Aims and Issues
massimo.bianchi@unibo.it

## Slide 2
PICAP Consortium |  |  |  | WP Nr. | Type of WP
1 | ITALY | University of Chieti Pescara UDA (Grant Holder) | UDA | WP5 | MANAGEMENT
2 | ITALY | SERINAR | SERINAR | WP4 | DISSEMINATION AND EXPLOITATION
3 | POLAND | Universytet Warszawski | OBA | WP1 | PREPARATION
4 | LITHUANIA | Vilnius Gedeminias Technical University | VGTU | WP2 | DEVELOPMENT
5 | RUSSIA | Astrakan State University | ASU | WP2 | DEVELOPMENT
6 | RUSSIA | Volgograd State Technical University | VSTU | WP4 | DISSEMINATION AND EXPLOITATION
7 | KAZAKHSTAN | Caspian State University of Technologies and Engineering Named After Sh. Yessenov | CSUTE | WP3 | QUALITY PLAN
8 | KAZAKHSTAN | University of International Business | UIB | WP3 | QUALITY PLAN
9 | AZERBAIJAN | Azerbaijan Tourism and Management University | ATMU | WP1 | PREPARATION
10 | AZERBAIJAN | Khazar University Baku | KHAZAR |  | 
11 | AZERBAIJAN | MIRAS Association | MIRAS |  | 
Ass. 1 | LITHUANIA | JSC GET WEB | GetWeb |  | Associate Partners
Ass. 2 | GERMANY | Europen- PEN | Europen |  | 
Ass 3 | ITALIA | Istituto Centrale per l’Archeologia | ICA |  | 

## Slide 3
PICAP Consortium |  |  |  | WP Nr. | Type of WP
P 1 | ITALY | University of Chieti Pescara UDA (Grant Holder) | UDA | WP5 | MANAGEMENT
P 9 | AZERBAIJAN | Azerbaijan Tourism and Management University | ATMU | WP1 | PREPARATION
P 3 | POLAND | Universytet Warszawski | OBA | WP1 | 
P 5 | RUSSIA | Astrakan State University | ASU | WP2 | DEVELOPMENT
P 4 | LITHUANIA | Vilnius Gedeminias Technical University | VGTU | WP2 | 
P 7 | KAZAKHSTAN | Caspian State University of Technologies and Engineering Named After Sh. Yessenov | CSUTE | WP3 | QUALITY PLAN
P 8 | KAZAKHSTAN | University of International Business | UIB | WP3 | 
P 6 | RUSSIA | Volgograd State Technical University | VSTU | WP4 | DISSEMINATION AND EXPLOITATION
P 2 | ITALY | SERINAR | SERINAR | WP4 | 
P 10 | AZERBAIJAN | Khazar University Baku | KHAZAR |  | 
P 11 | AZERBAIJAN | MIRAS Association | MIRAS |  | 
Ass. 1 | LITHUANIA | JSC GET WEB | GetWeb |  | Associate Partners
Ass. 2 | GERMANY | Europen- PEN | Europen |  | 
Ass 3 | ITALIA | Istituto Centrale per l’Archeologia | ICA |  | 

## Slide 4
 | PROGRAMME COUNTRY | = |  |  |  |  | 
 | PARTNER COUNTRY | X |  |  |  |  | 
 |  |  | feb-21 | mar-21 | apr-21 | mag-21 | REMARKS
Ref | Dscrpt | Weeks | M1 | M2 | M3 | M4 | 
1 | PREPARATION |  |  |  |  |  | 
1.1. | Review of UE best practices of PE and MOOCS and Partner Countries courses programs | 12 |  | 3X= | 3X= | 3X= | 
1.2. | Meetings with local key institutions and enterprises for professional profile | 4 |  |  |  | 2X | Add local professionals.Organize visits in Distance or Presence
1.4. | Building basic framework of professional profiles and skills | 6 |  |  |  | 2X | Organize visits in Distance or Presence
1.5. | Improving PE Enterprise Classrooms, Laboratories and MOOCs Platforms | 12 |  |  |  |  | Organize visits in Distance or Presence
2 | DEVELOPMENT |  |  |  |  |  | 
2.2. | Development of Curricula and Syllabi | 8 | 2= | 2X= | 2X= | 2X= | Basic on Modules, Courses and Masters
3 | QUALITY PLAN |  |  |  |  |  | 
3.1. | Handbook on Quality Assurance | 4 |  |  | 2= | 2= | 
4 | DISSEMINATION AND EXPLOITATION |  |  |  |  |  | 
4.2. | Website establishment and updating | 22 |  |  | 2X= | 2X= | 
4.3. | Production of Printed and Electronic Dissemination Materials and Publications | 6 |  |  |  | 2X | PE Handbook
4.4. | Conferences, workshops and InterProject Meetings | 12 |  |  |  | 2X | With EUROTECH, HEIPNET and BECK
5 | MANAGEMENT |  |  |  |  |  | 
5.1. | General Project Governance | 24 | 2X | 2X | 2X | 2X | 
5.2. | Consolidated Work Plan and Project Management Handbook | 6 | 2X | 2X= | 2X= |  | 
5.3. | Designing Logo, Project Concept and P.Website | 6 | 2X | 2X= | 2X= |  | 
5.4. | Development of the Project Structure | 6 | 2X | 2X= | 2X= |  | 

## Slide 5
The main objective of WP PREPARATION is to organize the implementation of Pilot Courses Programmes.
This is the most critical WP as it refers to the creation of the conditions for Pilot Courses realization with a particular focus on teaching staff to manage Practice Management classrooms.
The main output of the WP1 is the review of the curricula, and of the didactical offer of courses on SMEs Entrepreneurship and Management according to market needs and the increasing of attractiveness of courses related to these subjects, by the introduction of active didactics focused on tight links between theory and practice.
WP 1
PREPARATION ATMU / OBA

## Slide 6
Following the accomplishment of WP1 with the review of Partners curricula, on CH and tourism, the project will go on with the implementation of the Pilot Courses in PC.
The Development of Pilot Courses, divided into Short and Curricular Courses will be shared among PC as follows :
WP 2
DEVELOPMENT ASU / VGTU
Country Area | PC | Short Courses | Curricular Courses 1st, 2nd Level | Teachers | Tutors | Menthors | Students
AZ | ATMU | 2 | 1 | 3 | 6 | 3 | 50
 | KHAZAR | 2 | 1 | 3 | 6 | 3 | 50
RU | ASU | 2 | 1 | 3 | 6 | 3 | 50
 | VSTU | 2 | 1 | 3 | 6 | 3 | 50
KZ | CSUTE | 2 | 1 | 3 | 6 | 3 | 100
 | UIB | 10 | 5 | 15 | 30 | 15 | 300

## Slide 7
INNOVATION IN DIDACTICS
Practice Enterprise PE
A Learning By Doing Approach in which students are committed to create, in the classroom and the support of teachers, tutors and menthors an enterprise with most of functions and realistic burdens and the connections with the net.
Massive Open On Line Courses MOOCS
massive open online course are on line courses aimed at unlimited participation and open access via theWeb .[In addition to traditional course materials, such as filmed lectures, readings, and probem sets, MOOCs provide interactive courses with user forums or social media discussions to support community interactions among students, professors, and Tutors as well as immediate feedback to quick quizzes and assignments

## Slide 8
SERINAR PE EXPERIENCES IN PROGRESS
PE Start Up
1. e-commerce X - Online support for the sale of goods to people / companies in financial difficulty
2. Quick Nuntium - Collection / dissemination of news for inexperienced surfers (Young and Seniors)
3. Online Real Estate Agency - for real estate sales with virtual tours
4. Right Now - Home delivery organization for small shops
Practice Enterprise MODULE UNIPV UNIBO
10 h 15 min
16°; 17°; 23° dec 2020
Teachers/Tutors
Maria Chiara Demartini UNIPV
Massimo Bianchi UNIBO
Daniele Gualdi UNIBO
Valentina Beretta UNICH

## Slide 9
In this Work Package the results of the PICASP project will be monitored by the participants directly involved in project activities as well as external parties. In consists in :
monitoring of the progress and achieved results in relation to the PICASP time schedule by coordinator;
monitoring of the results achieved by the teachers, administrative staff and students
feedback of the students, teachers, administrative staff and interested parties involved
reporting on the results of the internal and external PICASP monitoring with recommendations for enhancing project capacities.;
instructions for compliance management
WP 3
QUALITY PLAN CSUTE /UIB

## Slide 10
The main objective of this WP are to ensure
the general spreading of the project’s information
the extension of awareness about the project’s outcomes
the sustainability of project results
A variety of activities will be undertaken in order to fulfil these results:
Development of the dissemination plan with the aim of making sure that the project values and outputs reach target groups and wider public.
Dissemination through Electronic Resources: these will be very useful to rise to announce our project, to give regular updates of the progress of master programme development, and get students interested in it.
PICASP official web site will be created by UdA and will contain information on project results, news, events, training materials, relevant documents, promotion material and not commercial fund raising tools.
The websites of the applicant and partner institutions will be maintained and provides information related to the project events.
Reports and other document will be prepared on regular base and be posted on PICASP web site
WP 4
DISSEMINATION AND EXPLOITATION VSTU/SERINAR

## Slide 11
Dissemination Undertacken till now:
UDA –
    Press Conference
      - https://www.unich.it/news/conferenza-stampa-sui-progetti-erasmus-presentati-dalla-dannunzio
      -https://www.ilcentro.it/.../universit%
      -https://youtu.be/gOt4nMTb_MA
      -https://www.youtube.com/watch?v=gOt4nMTb_MA
    Interproject Meeting
Serinar –
  Information abot the project in the Network of Previous SERINAR / UNIBO Projects (
  Mail to the Azerbaijan Embassy of Rome (1)
  Mail to Members of the Italian Academy of Economics AIDEA (67)
  Mails to SVIMAP Network (88)
  Mails to ASSIOA (78)
MB
  The Sara’s Long Wave. Introduction to the II Vol Archaeologie. Una storia plurale. Studi e ricerche in memoria di Sara Santoro. Proceedings , University D’Annunzio - Chieti 7-9 November 2017 (In publishing)
  Le start up romagnole si specchiano nel Caspio ( The start-up of Emilia Romagna mirror themselves in the Caspian Sea). Resto del Carlino 26 sett 2020

## Slide 12
WP 5
PROJECT GOVERNANCE AND REPORTING UDA
PBM is responsible for the whole project management process and for activities developed by all participants. Project Coordinator Indicated by the Grant Holder (GH) chairs the PMB formed by the Project Coordinator, the GH Financial Manager, the representative of Partners and the Leaders of each WP all appointed on indication of Partners.
All project Bodies will be established in the Kickoff Meeting.
GH will appoint the GHF.
Coordinating committee of the associates partners chaired by the Project Coordinator Is composed by representatives of non associate partners. Peer Committee Team is composed 3 academic external members operating in the field of Management and Entrepreneurship nominated by the PC on indications of the G.Holder which will appoint also the Chair of the PRT. To the activity of PRT could participate Projet Partners without the right to vote but only to refer about project activities if invitated by PRT
The PEB is responsible for the execution and control of the project plan, the supporting educational and innovative activities, training, dissemination and budgets. PMB is the main decision making authority in charge to approve or disapprove any changes respect to the project plan, the budget, and the outcomes